| Risk - Uncertain or chance events that planning cannot overcome or control. - In the context of projects, risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on project objectives. A risk has a cause and, if it occurs, a consequence. - Project risk is an uncertain event or condition that, if it occurs, has an effect on at least one project objective. Risk Management: A proactive attempt to recognize and manage internal events and external threats that affect the likelihood of a project’s success. - What can go wrong (risk event). - How to minimize the risk event’s impact (consequences). - What can be done before an event occurs (anticipation). - What to do when an event occurs (contingency plans). Risk Management’s Benefits - A proactive rather than reactive approach. - Reduces surprises and negative consequences. - Prepares the project manager to take advantage of appropriate risks. - Provides better control over the future. - Improves chances of reaching project performance objectives within budget and on time. - Increase awareness of threats (early identification) - Improved ability to respond to the unexpected - Continuous improvement of product or services - Enhanced ability to profit from new opportunities - Improved management decision-making - Higher probability of achieving objectives - Enhanced stakeholder value - More effective use of resources The Risk Management Process - Risk Identify - Describe events that could negatively impact operations - Considers possible consequences should a risk event occur - Generate a list of possible risks through brainstorming, problem identification and risk profiling - Micro risk first, then specific events - Risk Assessment - Prioritize risk threats based on likelihood and severity - Determine acceptable levels of risk - Scenario analysis - Risk Assessment matrix - Failure Mode and Effective Analysis(FMEA) - Probability Analysis - Decision tree, NPV and PERT Risk Assessment Form. Risk Severity Matrix. | - Risk Response Development - Develop a strategy to reduce possible damage - Develop contingency plans - Mitigating Risk: - A systematic reduction in the extent of exposure to a risk and/or the likelihood of its occurrence. - Reducing impact of adverse even. - Also called risk reduction. - Determining Mitigation Plans - Understand the users and their needs. - Seek out the experts and use them. - Recognize risks that recur. - Encourage risk taking. - Recognize opportunities. - Encourage deliberate consideration of mitigation options. - Not all risks require mitigation plans. - Mitigation Plan Content - Determine the appropriate risk manager. - Develop a high-level mitigation strategy. - Identify actions and steps needed to implement the mitigation strategy. - Transferring Risk: Paying a premium to pass the risk to another party. It may make sense when the risk involves a narrow specialized area of expertise not normally found in program offices. But, transferring a risk to another organization can result in dependencies and loss of control that may have their own complications. Three of the most common risk transfers are: - Insurance - Product and service warranties - Transferring risks through business ownership - Avoiding Risk: Changing the project plan to eliminate the risk or condition. While the complete elimination of all risk is rarely possible, a risk avoidance strategy is designed to deflect as many threats as possible in order to avoid the costly and disruptive consequences of a damaging event. A risk avoidance methodology attempts to minimize vulnerabilities which can pose a threat. Risk avoidance and mitigation can be achieved through policy and procedure, training and education and technology implementations. - Sharing Risk: Allocating risk to different parties. Risk sharing doesn't mean pushing the threat of bad outcomes off on someone else. Rather, it means reducing the likelihood and impact of uncertainty. - Retaining Risk: Making a conscious decision to accept the risk. It is a risk management strategy under which a decision maker assumes all or part of a risk, instead of buying partial or full insurance or otherwise transferring risk (such as by hedging). - Risk Response Control - Risk Control - Identify potential root cause(s) of risk events - Perform gap analysis - Determine mitigation steps reduce risks to acceptable levels - Execution of the risk response strategy - Monitoring of triggering events - Initiating contingency plans - Watching for new risks - Establishing a Change Management System - Monitoring, tracking, and reporting risk - Fostering an open organization environment - Repeating risk identification/assessment exercises - Assigning and documenting responsibility for managing risk - Monitoring - Conduct regular monitoring to ensure risk mitigations are effective - Schedule regular risk reviews to identify new or changing risks | Contingency Plan - An alternative plan that will be used if a possible foreseen risk event actually occurs. - A plan of actions that will reduce or mitigate the negative impact (consequences) of a risk event. - Contingency planning is a tool and a process to anticipate and solve problem that typically arise during humanitarian response: - Analyze potential emergencies - Analyze potential impact - Establish clear objectives and strategies - Implement preparedness action - Risks of Not Having a Contingency Plan - Having no plan may slow managerial response. - Decisions made under pressure can be potentially dangerous and costly. Risk response matrix Contingency Funds: A contingency fund is cash or other assets reserved to address unforeseen circumstances or losses in a business. The role of the contingency fund is to improve a company's financial stability by developing a safety net that the firm can use to fill emergency needs. It can also be used to reduce the need to take out high-interest loans, such as credit cards, to cover unexpected expenses. - Funds to cover project risks — identified and unknown. Size of funds reflects overall risk of a project - Budget reserves: Are linked to the identified risks of specific work packages. - Management reserves: Are large funds to be used to cover major unforeseen risks (e.g., change in project scope) of the total project. Contingency Fund Estimate Time Buffers - Amounts of time used to compensate for unplanned delays in the project schedule. - The amount of time is dependent upon the inherent uncertainty of the project. The more uncertain the project the more time should be reserved for the schedule. The strategy is to assign extra time at critical moments in the project. - In the face of overall schedule uncertainty, buffers are sometimes added to the end of the project. |
| --- | --- | --- |