| Rationale for Reducing Project Duration - Customer requirements and contract commitments: Customer loyalty doesn’t (and can’t) truly exist, but customer commitment can and must be the goal for today’s and tomorrow’s best brands. Further, we have offered a way to assess a brand’s level of customer commitment, the Commitment Equation: Commitment level=level of satisfaction+ Attractiveness of Alternatives+ Level of Investment - Time-to-market pressures: Intense global competition and rapid technological advances have made speed a competitive advantage. To succeed, companies have to spot new opportunities, launch project teams, and bring new products or services to the marketplace in a flash. Perhaps in no industry does speed matter as much as in the electronics industry. Here are the top five market pressures that are driving this behavior: - Faster time to market and volume. - Tailored products for specific markets. - The quality imperative - The productivity vise. - Regulatory compliance - For example, the fate of U.S. auto industry depends in part on how quickly they shift their efforts to develop fuel-efficient, alternative forms of transportation. - Incentive contracts (bonuses for early completion) can make reducing project duration rewarding—usually for both the project contractor and owner. For example, a contractor finished a bridge across a lake 18 months early and received more than $6 million for the early completion. The availability of the bridge to the surrounding community 18 months early to reduce traffic gridlock made the incentive cost to the community seem small to users. If the marginal cost is less than Incentive then contractor can take the opportunity. - Unforeseen delays—for example, adverse weather, design flaws and equipment breakdown— cause substantial delays midway in the project. - Imposed deadlines- For example, a politician make a public statement that a new law building will be available in two years. Or the president of a software company remarks in a speech that new advanced software will be available in one year. Such statements too often become imposed project duration dates—without any consideration of the problems or cost of meeting such a date. - Overhead and public goodwill costs: More important, these increased costs of imposed duration dates are seldom recognized or noted by project participants. Sometimes very high overhead costs are recognized before the project begins. In these cases it is prudent to examine the direct costs of shortening the critical path versus the overhead cost savings. Usually there are opportunities to shorten a few critical activities at less than the daily overhead rate. Under specific conditions (which are not rare), huge savings are possible with little risk. - Pressure to move resources to other projects- There are times when it is important to reassign key equipment and/or people to new projects. Under these circumstances, the cost of compressing the project can be compared with the opportunity costs of not releasing key equipment or people. What are five common reasons for crashing a project? Reasons given could include: - Imposed deadline in which disfavor will be earned by not meeting superior’s deadline - Time to market competitive advantage - Realize benefits from incentive contracts - To make up for lost time and avoid contract penalties - Save extensive overhead costs - Free up resources to work on other projects - Exceed customer expectations. | Options for Accelerating Project completion/ 9 Easy Ways to Speed Up Project Delivery - Options When Resources Are Not Constrained - Adding Resources: The most common method for shortening project time is to assign additional staff and equipment to activities. There are limits, however, as to how much project delivery speed can be gained by adding staff. Doubling the size of the workforce will not necessarily reduce completion time by half. The relationship would be correct only when tasks can be partitioned so minimal communication is needed between workers, as in harvesting a crop by hand or repaving a highway. - Outsourcing Project Work: A common method for shortening the project time is to subcontract an activity. The subcontractor may have access to superior technology or expertise that will accelerate the completion of the activity. - Scheduling Overtime: The easiest way to add more labor to a project is not to add more people, but to schedule overtime. If a team works 50 hours week instead of 40, it might accomplish 20 percent more. By scheduling overtime you avoid the additional costs of coordination and communication encountered when new people are added. - Establish a Core Project Team: One of the advantages of creating a dedicated core team to complete a project is project delivery speed. Assigning professionals full time to a project avoids the hidden cost of multitasking in which people are forced to juggle the demands of multiple projects. - Do It Twice—Fast and Correctly: If you are in a hurry, try building a “quick and dirty” short-term solution, then go back and do it the right way. The additional costs of doing it twice are often more than compensated for by the benefits of satisfying the deadline. - Options When Resources Are Constrained - Fast-Tracking: Sometimes it is possible to rearrange the logic of the project network so that critical activities are done in parallel (concurrently) rather than sequentially. This alternative is a good one if the project situation is right. When this alternative is given serious attention, it is amazing to observe how creative project team-members can be in finding ways to restructure sequential activities in parallel. - Critical-Chain: Critical-chain project management (CCPM) is designed to accelerate project completion. The jury is still out in terms of its applicability. Still CCPM principles appear sound and worthy of experimentation if project delivery speed is essential. - Reducing Project Scope: Probably the most common response for meeting unattainable project delivery deadlines is to reduce or scale back the scope of the project. This invariably leads to a reduction in the functionality of the project. - Compromise Quality: Reducing quality is always an option, but it is rarely acceptable or used. If quality is sacrificed, it may be possible to reduce the time of an activity on the critical path. What if Cost, Not Time Is the Issue? - Commonly Used Options for Cutting Costs - Reduce project scope - Have owner take on more responsibility - Outsourcing project activities or even the entire project - Brainstorming cost savings options | Explanation of Project costs - Project Indirect Costs - Costs that cannot be associated with any particular work package or project activity. - Ex: Supervision, administration, consultants and interest - Costs that vary (increase) with time - Ex: Reducing project time directly reduces indirect costs. - Indirect costs benefit multiple project - Indirect Cost would include the cost of supporting the purchasing process and the purchased product. - Examples of indirect costs include the costs of: - Management - General administration - Building rental - Utilities - Security - Advertisement - Insurance - Legal - Project Direct Costs - Normal costs that can be assigned directly to a specific work package or project activity - Ex: labor, materials, equipment, and subcontractors - Crashing activities increases direct costs - Direct costs directly benefit a particular project - Direct Cost would include the actual cost of purchasing the product - Examples of direct costs include: - Employee salaries and benefits - Labor costs - Materials costs - Equipment rental costs - Project related travel costs Identifying direct costs to reduce project time - Gather information about direct and indirect costs of specific project durations. costs of specific project durations - Search critical activities for lowest direct-cost activities to shorten project duration. - Compute total costs for specific durations and compare to benefits of reducing project time. Constructing a Project cost -Duration Graph - Find total direct costs for selected project durations - Find total indirect costs for selected project durations - Sum direct and indirect costs for these selected project durations - Compare additional cost alternatives for benefits - Determining Activities to shorten - Shorten the activities with the smallest increase in cost per unit of time - Assumptions: - The cost relationship is linear. - Normal time assumes low-cost, efficient methods to complete the activity. - Crash time represents a limit- the greatest time reduction possible under realistic conditions. - Slope represents a constant cost per unit of time. Slope=(Crash Cost-Normal Cost)/(Normal Time-Crash Time) - All accelerations must occur within the normal and crash times. |
| --- | --- | --- |